## Sheet1
Gantt Chart
Phase 1 | Duration | Start Date | End Date
Paper Sketch | 3 | 2018-01-09 | 2018-01-11
Network Map | 4 | 2018-01-12 | 2018-01-15
IP Adressing Schemes | 3 | 2018-01-16 | 2018-01-18
Prepare Equipment | 2 | 2018-01-19 | 2018-01-20
Presentation Phase 1 | 1 | 2018-01-26 | 2018-01-26
Phase 2
Initializing Devices | 3 | 2018-01-21 | 2018-01-23
Configure Ports | 2 | 2018-01-24 | 2018-01-25
Testing & Troubleshooting | 3 | 2018-01-26 | 2018-01-28
Configure a Dynamic Routing Protocol | 3 | 2018-01-29 | 2018-01-31
Record Specs of serveral machines | 2 | 2018-02-01 | 2018-02-02
Setup TFTP Server | 2 | 2018-02-03 | 2018-02-04
Presentation Phase 2 | 1 | 2018-02-06 | 2018-02-06
Phase 3
Create Cloning Server | 4 | 2018-02-05 | 2018-02-08
Using Sysprep | 3 | 2018-02-09 | 2018-02-11
Multicast cloning | 4 | 2018-02-12 | 2018-02-15
Setup Primary Domain Controller | 2 | 2018-02-16 | 2018-02-17
Setup clients to login to the AD server | 3 | 2018-02-26 | 2018-02-28
Setup backup Domain Controller | 2 | 2018-03-01 | 2018-03-02
Protoype a machine | 1 | 2018-03-02 | 2018-03-02
Presentation Phase 3 | 1 | 2018-04-03 | 2018-04-03
Phase 4
Configure Vlans | 1 | 2018-04-05 | 2018-04-05
Restricting the flow of traffic(ACL) | 1 | 2018-04-05 | 2018-04-05
Setup Streaming Machines | 2 | 2018-04-07 | 2018-04-10
Configure Printer Pool | 2 | 2018-04-12 | 2018-04-13
Configure NTP and logging | 1 | 2018-04-17 | 2018-04-17
Finishing Touches | 1 | 2018-04-18 | 2018-04-18
Presentation Phase 4 | 1 | 2018-04-26 | 2018-04-26
Documentation | Concurrently | 2018-01-09 | 2018-04-15
Total Duration | 60
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.